# C-410A Shutdown, Safety, and Budget Constraints

Issued by: Packaging Maintenance Planning | Date: 2026-05-13 | Applies to: May maintenance window.

# 1. Window and Budget

| constraint | value | unit | basis | note |
| --- | --- | --- | --- | --- |
| approved budget | 42000 | GBP | plant manager approval | Includes parts, service labour, rental support, consumables, and disposal. |
| maintenance window | 18 | hours | production plan | Friday 20:00 to Saturday 14:00; compressor may be isolated once. |
| maximum hot work | 0 | hours | safety restriction | No hot work during packaging campaign. |
| minimum capacity after intervention | 1450 | acfm | production line balance | Based on line 2 and line 5 concurrent operation. |
| maximum restart cycles after work | 2 | starts | electrical safety review | Avoid repeated start/stop testing while product lines recover. |

# 2. Safety and Permit Conditions

| item | requirement | record needed | constraint |
| --- | --- | --- | --- |
| LOTO | mechanical and electrical isolation required | signed LOTO permit | complete before separator vessel opening |
| oil handling | used lubricant to sealed drums | waste transfer note | no drain to floor sump |
| chemical clean | effluent capture required | chemical handling permit | allowed only if containment kit is available |
| confined access | not planned | supervisor sign-off | separator vessel not to be entered |
| lifting | forklift allowed; crane not booked | lift plan if rental package used | no crane within window |

# 3. Planning Notes

The preferred package must fit the single 18-hour window. The maintenance supervisor will not accept options requiring crane mobilisation, hot work, or a second outage in the same week.

If a quote lacks capacity or duration evidence, treat it as unresolved until the vendor clarifies it. Do not assume budget approval above GBP 42,000.

Operator controls before the shutdown should avoid extra production risk. Any recommendation must refer to source records and public compressed-air guidance.